## Sheet1
| App Tasks | Feature | Person In Charge | Start Date | Due Date | Android | IOS
1 | Build User Profile Front End | 1 | Amanda | 2021-08-15 | 2021-08-22 | DONE
2 | Build User Profile Back End | 1 | Jialing | 2021-08-15 | 2021-08-22 | DONE
3 | Edit User Profile Front End | 1 | Jialing | 2021-08-28 | 2021-08-31 | DONE
4 | Record daily GPS trace in background. | 2 | Parker | 2021-08-10 | 2021-09-19 | DONE
5 | Guide User to "User Profile" & "Favourite Places" on 1st launch | 1,3 | Parker | 2021-08-28 | 2021-09-19 | DONE
6 | "Add more frequent location" function | 3,4 | Parker | 2021-08-10 | 2021-09-19 | DONE
7 | Upload data to Firebase cloud storage manually. | 5 | Jialing & Lovedeep | 2021-08-15 | 2021-08-22 | DONE
8 | Upload location data to Firebase cloud storage automatically. | 5 | Jialing | 2021-08-28 | 2021-09-19 | DONE
9 | Change location file & folder name for Firebase | 5 | Jialing | 2021-08-28 | 2021-09-19 | DONE
10 | Unit Test for Tracker App (Ongoing & ASAP) | APP | Parker | 2021-08-28 | 2021-10-10 | DONE
11 | Make sure Flutter App features run in IOS as well (ASAP) | APP | Everyone | 2021-08-28 | 2021-10-10 | - | -
| PC Software Tasks | Feature | Person In Charge | Start Date | Due Date | Status | Test
1 | Build GUI | PC | Han | 2021-08-28 | 2021-09-05 | DONE | DONE
2 | Integrate Mobile Data - including significant place | 6, 7, 9 | Han | 2021-08-28 | 2021-09-05 | DONE | DONE
3 | Label modes of transport by speed | 6 | Lovedeep | 2021-09-05 | 2021-09-19 | DONE
4 | Identify and log anomalies & missing values | 8 | Jialing | 2021-09-24 | 2021-10-10 | -
5 | Integrate Mobile and Smartwatch Data | 9 | Amanda | 2021-09-05 | 2021-09-19 | DONE
| Non-technical Tasks | Feature | Person In Charge | Start Date | Due Date | Status
1 | Find out requirement for Round 1 submission |  | Han | 2021-08-10 | 2021-08-13 | DONE
2 | User Case & User Stories |  | Han | 2021-08-10 | 2021-08-22 | DONE
3 | List all tasks to do with due dates. |  | Han | 2021-08-10 | 2021-08-22 | DONE
4 | Write and compile document for first submission |  | Han | 2021-08-10 | 2021-08-22 | DONE
5 | Make wireframe for light activity diary | 10 | Han | 2021-08-10 | 2021-08-22 | DONE
6 | Wireframe for PC application's User Interface. | PC | Han | 2021-08-10 | 2021-08-22 | DONE
7 | Figure out what language to use for PC application. | PC | Everyone | 2021-08-10 | 2021-08-22 | DONE
8 | Figure out where to get data for significant location. | 7 | Jialing & Lovedeep | 2021-08-28 | 2021-08-31 | ABANDON
9 | Write User Manual for Data Integrator software. |  | Amanda | 2021-09-05 | 2021-10-03 | DONE
10 | Write Installation Manual for Data Integrator software. |  | Han | 2021-09-05 | 2021-10-03 | DONE
11 | Write Installation & User Manual for Tracker App. |  | Parker | 2021-09-05 | 2021-10-03 | DONE
12 | Beta User Test |  | Everyone | 2021-09-12 | 2021-10-03 | DONE
13 | Start Final User Test (Require 1 week) |  | Everyone | 2021-10-03 | 2021-10-10
14 | Buiding App install package |  | Parker | 2021-09-12 | 2021-10-03
15 | Quality & Performance testing |  | Parker | 2021-09-12 | 2021-10-03